## data
finding_id | model_id | validation_id | title | description | severity | category | status | owner_id | raised_date | due_date | closed_date | root_cause | management_response | remediation_action
F-0001 | M-0012 | V-0013 | CRE obligor data gap | Segment B data quality gap: 14% of obligor financial statements missing in construction lending. | Critical | Data | Open | U-101 | 2026-07-22 | 2026-08-21
F-0002 | M-0012 | V-0013 | Macro overlay undocumented | Model documentation does not reflect the December parameter update to the macro overlay. | Medium | Documentation | Open | U-101 | 2026-08-01 | 2026-11-14
F-0003 | M-0015 | V-0017 | LGD floor deviation | LGD floor methodology deviates from policy. | Medium | Methodology | Open | U-103 | 2026-08-01 | 2026-10-20
F-0004 | M-0015 | V-0017 | Collateral valuation lag | Collateral valuation lag above 90 days for 8% of the retail mortgage portfolio. | Critical | Data | Open | U-103 | 2026-08-01 | 2026-09-18
F-0005 | M-0031 | V-0046 | Scenario weights stale | Macro scenario weights reflect prior-year ALCO assumptions and need committee refresh. | Medium | Methodology | Open | U-109 | 2026-08-01 | 2026-10-30
F-0006 | M-0031 | V-0046 | Q-factor evidence missing | Q-factor documentation incomplete for the CRE segment. | Medium | Documentation | Open | U-109 | 2026-08-01 | 2026-11-24
F-0007 | M-0038 | V-0057 | Stage 2 triggers | Stage 2 trigger calibration needs a post-pandemic refresh; thresholds over-stage by about 15%. | Critical | Methodology | Open | U-112 | 2026-08-01 | 2026-10-18
F-0008 | M-0038 | V-0057 | Cross-border staging | GBP and EUR books apply different SICR definitions. | Medium | Data | Open | U-112 | 2026-08-01 | 2026-11-09
F-0009 | M-0038 | V-0057 | Disclosure template gap | Pillar 3 disclosure table not aligned to the current template. | Medium | Documentation | Open | U-112 | 2026-08-01 | 2026-12-09
F-0010 | M-0042 | V-0063 | NMD behaviour assumptions | Repricing beta assumes 60% pass-through against 72% observed. | Medium | Methodology | Open | U-115 | 2026-08-01 | 2026-09-22
F-0011 | M-0048 | V-0075 | Intraday data gap | Four-hour gap in real-time position data from APAC operations. | Medium | Data | Open | U-118 | 2026-08-01 | 2026-10-25
F-0012 | M-0071 | V-0118 | NII rate path | NII component needs rate-path recalibration: +200bp shock 15% above benchmark. | Critical | Methodology | Open | U-127 | 2026-08-01 | 2026-10-12
F-0013 | M-0071 | V-0118 | Fee income assumptions | Fee income projection uses undocumented AUM growth assumptions. | Medium | Documentation | Open | U-127 | 2026-08-01 | 2026-11-04
F-0014 | M-0071 | V-0118 | Trading tail risk | Trading revenue tail risk underestimated; 99th percentile exceedances twice the expected rate. | Critical | Methodology | Open | U-127 | 2026-08-01 | 2026-10-12
F-0015 | M-0071 | V-0118 | UAT sign-off | UAT sign-off delayed by a core banking interface dependency. | Medium | Implementation | In Progress | U-127 | 2026-08-01 | 2026-10-20
F-0016 | M-0076 | V-0125 | CRE loss rates stale | CRE loss rates based on 2019 vintage data; no post-pandemic structural update. | Critical | Data | Open | U-130 | 2026-08-01 | 2026-10-15
F-0017 | M-0076 | V-0125 | Auto loan recalibration | Auto loan delinquency transition matrix not updated; subprime performance has diverged. | Critical | Methodology | Open | U-130 | 2026-08-01 | 2026-10-15
F-0018 | M-0076 | V-0125 | Static correlations | Cross-portfolio correlation uses static assumptions with no tail dependence. | Medium | Methodology | Open | U-130 | 2026-08-01 | 2026-11-19
F-0019 | M-0076 | V-0125 | Scenario mapping | Unemployment, HPI and commercial vacancy not mapped to supervisory scenario variables. | Medium | Data | Open | U-130 | 2026-08-01 | 2026-11-19
F-0020 | M-0076 | V-0125 | Sensitivity section | Documentation lacks the sensitivity analysis section required by policy 4.2.3. | Low | Documentation | Open | U-130 | 2026-08-01 | 2026-12-19
F-0021 | M-0078 | V-0127 | RWA linkage | Credit risk RWA feed into the capital projection is unreconciled. | Critical | Methodology | Open | U-101 | 2026-08-01 | 2026-10-10
F-0022 | M-0078 | V-0127 | Capital actions | Dividend and buyback assumptions are undocumented. | Medium | Documentation | Open | U-101 | 2026-08-01 | 2026-11-09
F-0023 | M-0078 | V-0127 | Payout ratio conflict | Dividend payout ratio assumption conflicts with the board-approved capital plan. | Medium | Methodology | Open | U-101 | 2026-08-01 | 2026-11-09
F-0024 | M-0018 | V-0022 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Securities Portfolio Prepayment Model). | Medium | Performance | Closed | U-201 | 2026-06-23 | 2027-01-25 | 2026-09-30
F-0025 | M-0018 | V-0022 | Production code differs from the validated version | Production code differs from the validated version (Securities Portfolio Prepayment Model). | Medium | Implementation | In Progress | U-201 | 2026-02-16 | 2026-09-14
F-0026 | M-0020 | V-0026 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Commercial & Industrial LGD Model). | Critical | Performance | In Progress | U-203 | 2025-12-09 | 2026-03-04
F-0027 | M-0020 | V-0026 | Segmentation not revisited since development | Segmentation not revisited since development (Commercial & Industrial LGD Model). | Medium | Methodology | Open | U-203 | 2025-11-17 | 2026-02-07
F-0028 | M-0020 | V-0026 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial & Industrial LGD Model). | Low | Data | Open | U-203 | 2026-08-30 | 2027-03-08
F-0029 | M-0021 | V-0028 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Consumer Capital Model). | Critical | Performance | In Progress | U-204 | 2026-04-13 | 2026-06-12
F-0030 | M-0021 | V-0028 | Production code differs from the validated version | Production code differs from the validated version (Consumer Capital Model). | Medium | Implementation | Open | U-204 | 2025-11-28 | 2026-06-10
F-0031 | M-0021 | V-0028 | Segmentation not revisited since development | Segmentation not revisited since development (Consumer Capital Model). | Low | Methodology | Closed | U-204 | 2026-07-17 | 2027-03-02 | 2026-09-30
F-0032 | M-0022 | V-0030 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Residential Mortgage LGD Model). | Low | Performance | Closed | U-202 | 2026-03-26 | 2026-09-16 | 2026-09-01
F-0033 | M-0022 | V-0030 | Production code differs from the validated version | Production code differs from the validated version (Residential Mortgage LGD Model). | Medium | Implementation | Open | U-202 | 2025-09-28 | 2026-01-27
F-0034 | M-0022 | V-0030 | Production code differs from the validated version | Production code differs from the validated version (Residential Mortgage LGD Model). | Medium | Implementation | Open | U-202 | 2026-08-13 | 2027-01-30
F-0035 | M-0025 | V-0036 | Assumption log incomplete | Assumption log incomplete (Non-maturity Deposit Prepayment Model). | Low | Documentation | Closed | U-205 | 2026-08-02 | 2027-01-23 | 2026-09-30
F-0036 | M-0028 | V-0042 | Segmentation not revisited since development | Segmentation not revisited since development (Operating Expense Revenue Model). | Critical | Methodology | Open | U-205 | 2026-08-09 | 2027-01-13
F-0037 | M-0028 | V-0042 | Segmentation not revisited since development | Segmentation not revisited since development (Operating Expense Revenue Model). | Medium | Methodology | Closed | U-205 | 2026-06-14 | 2026-08-16 | 2026-07-28
F-0038 | M-0028 | V-0042 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Operating Expense Revenue Model). | Medium | Performance | Open | U-205 | 2025-11-26 | 2026-05-10
F-0039 | M-0029 | V-0044 | Segmentation not revisited since development | Segmentation not revisited since development (Mortgage ALM/IRR Model). | Low | Methodology | Open | U-007 | 2026-08-18 | 2026-11-14
F-0040 | M-0029 | V-0044 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Mortgage ALM/IRR Model). | Low | Performance | In Progress | U-007 | 2026-08-24 | 2027-04-07
F-0041 | M-0033 | V-0049 | Assumption log incomplete | Assumption log incomplete (Securities Portfolio Funds transfer pricing Model v2). | Low | Documentation | Closed | U-203 | 2025-12-27 | 2026-06-28 | 2026-06-04
F-0042 | M-0039 | V-0059 | Assumption log incomplete | Assumption log incomplete (Branch Volume Model). | Medium | Documentation | In Progress | U-206 | 2025-09-23 | 2026-01-06
F-0043 | M-0039 | V-0059 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Branch Volume Model). | Medium | Data | In Progress | U-206 | 2026-04-11 | 2026-11-21
F-0044 | M-0039 | V-0059 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Branch Volume Model). | Medium | Performance | Open | U-206 | 2026-05-17 | 2026-10-12
F-0045 | M-0043 | V-0065 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Deposit Volume Revenue Model). | Medium | Performance | In Progress | U-205 | 2026-07-22 | 2026-12-14
F-0046 | M-0043 | V-0065 | Assumption log incomplete | Assumption log incomplete (Deposit Volume Revenue Model). | Medium | Documentation | Open | U-205 | 2026-04-16 | 2026-09-08
F-0047 | M-0043 | V-0065 | Assumption log incomplete | Assumption log incomplete (Deposit Volume Revenue Model). | Medium | Documentation | Closed | U-205 | 2025-09-13 | 2026-02-13 | 2026-01-18
F-0048 | M-0049 | V-0077 | Production code differs from the validated version | Production code differs from the validated version (Credit Card LGD Model). | Medium | Implementation | Closed | U-205 | 2026-03-21 | 2026-10-22 | 2026-09-28
F-0049 | M-0049 | V-0077 | Segmentation not revisited since development | Segmentation not revisited since development (Credit Card LGD Model). | Medium | Methodology | Open | U-205 | 2026-03-21 | 2026-06-25
F-0050 | M-0049 | V-0077 | Assumption log incomplete | Assumption log incomplete (Credit Card LGD Model). | Critical | Documentation | Closed | U-205 | 2026-01-02 | 2026-06-25 | 2026-06-13
F-0051 | M-0050 | V-0079 | Production code differs from the validated version | Production code differs from the validated version (Wealth Lending PD Model). | Medium | Implementation | Open | U-205 | 2026-04-24 | 2026-12-16
F-0052 | M-0050 | V-0079 | Production code differs from the validated version | Production code differs from the validated version (Wealth Lending PD Model). | Critical | Implementation | In Progress | U-205 | 2026-06-28 | 2027-02-20
F-0053 | M-0051 | V-0081 | Segmentation not revisited since development | Segmentation not revisited since development (Branch Climate Model). | Medium | Methodology | Open | U-201 | 2026-09-08 | 2027-01-15
F-0054 | M-0053 | V-0085 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Credit Card Rating Model). | Medium | Performance | Open | U-007 | 2026-03-19 | 2026-09-13
F-0055 | M-0053 | V-0085 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Credit Card Rating Model). | Low | Performance | Open | U-007 | 2026-03-30 | 2026-10-19
F-0056 | M-0053 | V-0085 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Credit Card Rating Model). | Medium | Data | Closed | U-007 | 2026-05-23 | 2026-11-17 | 2026-09-30
F-0057 | M-0054 | V-0087 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Card Q-factor Model). | Critical | Performance | Closed | U-203 | 2025-09-18 | 2026-01-11 | 2025-12-14
F-0058 | M-0054 | V-0087 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Card Q-factor Model). | Low | Data | Closed | U-203 | 2026-01-29 | 2026-05-02 | 2026-04-19
F-0059 | M-0063 | V-0103 | Segmentation not revisited since development | Segmentation not revisited since development (Net Interest Income Balance Model). | Medium | Methodology | Open | U-007 | 2026-07-15 | 2027-02-21
F-0060 | M-0065 | V-0107 | Assumption log incomplete | Assumption log incomplete (Securities Reserve allocation Model). | Medium | Documentation | Closed | U-204 | 2026-06-18 | 2026-10-04 | 2026-09-05
F-0061 | M-0067 | V-0111 | Assumption log incomplete | Assumption log incomplete (Auto Loan EAD Model). | Medium | Documentation | Open | U-205 | 2025-09-04 | 2026-01-27
F-0062 | M-0067 | V-0111 | Production code differs from the validated version | Production code differs from the validated version (Auto Loan EAD Model). | Low | Implementation | Open | U-205 | 2026-07-03 | 2027-02-01
F-0063 | M-0067 | V-0111 | Production code differs from the validated version | Production code differs from the validated version (Auto Loan EAD Model). | Medium | Implementation | Open | U-205 | 2026-02-01 | 2026-09-02
F-0064 | M-0072 | V-0120 | Segmentation not revisited since development | Segmentation not revisited since development (Commercial & Industrial EAD Model). | Medium | Methodology | Open | U-205 | 2026-04-04 | 2026-10-25
F-0065 | M-0074 | V-0122 | Production code differs from the validated version | Production code differs from the validated version (Credit Card Scorecard Model). | Low | Implementation | Open | U-204 | 2026-01-20 | 2026-08-22
F-0066 | M-0074 | V-0122 | Production code differs from the validated version | Production code differs from the validated version (Credit Card Scorecard Model). | Critical | Implementation | In Progress | U-204 | 2025-09-10 | 2025-11-28
F-0067 | M-0075 | V-0124 | Segmentation not revisited since development | Segmentation not revisited since development (Treasury ALM/IRR Model v2). | Low | Methodology | Open | U-205 | 2026-06-23 | 2026-09-28
F-0068 | M-0081 | V-0129 | Assumption log incomplete | Assumption log incomplete (Dealer Floorplan Rating Model). | Low | Documentation | Closed | U-205 | 2026-02-26 | 2026-07-12 | 2026-06-23
F-0069 | M-0081 | V-0129 | Segmentation not revisited since development | Segmentation not revisited since development (Dealer Floorplan Rating Model). | Medium | Methodology | Open | U-205 | 2026-03-05 | 2026-09-21
F-0070 | M-0084 | V-0133 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Deposit Volume Volume Model). | Medium | Performance | Open | U-204 | 2026-07-28 | 2027-02-23
F-0071 | M-0084 | V-0133 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Deposit Volume Volume Model). | Medium | Data | Closed | U-204 | 2025-10-30 | 2026-02-20 | 2026-01-21
F-0072 | M-0084 | V-0133 | Production code differs from the validated version | Production code differs from the validated version (Deposit Volume Volume Model). | Critical | Implementation | In Progress | U-204 | 2025-10-07 | 2026-04-11
F-0073 | M-0090 | V-0141 | Assumption log incomplete | Assumption log incomplete (Securities Q-factor Model). | Critical | Documentation | Closed | U-206 | 2026-05-16 | 2026-07-31 | 2026-07-11
F-0074 | M-0090 | V-0141 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Securities Q-factor Model). | Medium | Data | Closed | U-206 | 2026-04-26 | 2026-07-16 | 2026-06-19
F-0075 | M-0093 | V-0145 | Segmentation not revisited since development | Segmentation not revisited since development (Trading Book RWA Model v2). | Low | Methodology | Open | U-201 | 2026-01-26 | 2026-06-17
F-0076 | M-0093 | V-0145 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Trading Book RWA Model v2). | Medium | Performance | Open | U-201 | 2025-08-26 | 2026-02-19
F-0077 | M-0096 | V-0151 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Securities Portfolio Liquidity Model). | Medium | Data | Open | U-205 | 2026-04-07 | 2026-11-14
F-0078 | M-0096 | V-0151 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Securities Portfolio Liquidity Model). | Low | Data | Open | U-205 | 2026-01-08 | 2026-04-06
F-0079 | M-0096 | V-0151 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Securities Portfolio Liquidity Model). | Medium | Data | Open | U-205 | 2025-10-07 | 2026-04-19
F-0080 | M-0097 | V-0153 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Credit Card EAD Model v2). | Low | Performance | Closed | U-201 | 2025-09-03 | 2026-04-30 | 2026-04-06
F-0081 | M-0097 | V-0153 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Credit Card EAD Model v2). | Low | Performance | Closed | U-201 | 2025-10-04 | 2025-12-03 | 2025-11-26
F-0082 | M-0102 | V-0161 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial IFRS 9 Model). | Medium | Data | Closed | U-003 | 2026-04-13 | 2026-12-02 | 2026-09-30
F-0083 | M-0102 | V-0161 | Production code differs from the validated version | Production code differs from the validated version (Commercial IFRS 9 Model). | Medium | Implementation | Open | U-003 | 2026-08-31 | 2027-03-11
F-0084 | M-0104 | V-0165 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Small Business EAD Model). | Medium | Performance | Open | U-204 | 2026-07-06 | 2026-09-04
F-0085 | M-0104 | V-0165 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Small Business EAD Model). | Critical | Performance | Open | U-204 | 2025-10-22 | 2026-01-13
F-0086 | M-0104 | V-0165 | Segmentation not revisited since development | Segmentation not revisited since development (Small Business EAD Model). | Low | Methodology | Open | U-204 | 2025-11-18 | 2026-04-01
F-0087 | M-0108 | V-0173 | Production code differs from the validated version | Production code differs from the validated version (Deposit Volume Climate Model). | Low | Implementation | Closed | U-206 | 2026-01-21 | 2026-08-22 | 2026-08-01
F-0088 | M-0108 | V-0173 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Deposit Volume Climate Model). | Medium | Data | In Progress | U-206 | 2025-09-03 | 2025-11-16
F-0089 | M-0108 | V-0173 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Deposit Volume Climate Model). | Medium | Performance | Closed | U-206 | 2025-09-01 | 2026-01-28 | 2026-01-21
F-0090 | M-0112 | V-0179 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Small Business Rating Model). | Medium | Performance | Open | U-201 | 2026-03-28 | 2026-08-26
F-0091 | M-0112 | V-0179 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Small Business Rating Model). | Medium | Performance | Open | U-201 | 2026-05-17 | 2026-09-07
F-0092 | M-0115 | V-0184 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Student Lending EAD Model). | Low | Data | Closed | U-203 | 2026-08-12 | 2027-02-05 | 2026-09-30
F-0093 | M-0115 | V-0184 | Assumption log incomplete | Assumption log incomplete (Student Lending EAD Model). | Medium | Documentation | Open | U-203 | 2025-12-03 | 2026-06-21
F-0094 | M-0117 | V-0188 | Production code differs from the validated version | Production code differs from the validated version (Trading Book Scenario Model). | Medium | Implementation | Closed | U-206 | 2025-12-12 | 2026-06-13 | 2026-06-03
F-0095 | M-0118 | V-0190 | Production code differs from the validated version | Production code differs from the validated version (Consumer Reserve allocation Model). | Medium | Implementation | In Progress | U-206 | 2026-01-13 | 2026-06-11
F-0096 | M-0118 | V-0190 | Segmentation not revisited since development | Segmentation not revisited since development (Consumer Reserve allocation Model). | Medium | Methodology | In Progress | U-206 | 2026-04-17 | 2026-08-15
F-0097 | M-0118 | V-0190 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Consumer Reserve allocation Model). | Medium | Data | Open | U-206 | 2025-10-19 | 2026-03-22
F-0098 | M-0122 | V-0193 | Assumption log incomplete | Assumption log incomplete (Net Interest Income Volume Model v2). | Critical | Documentation | Closed | U-202 | 2026-01-22 | 2026-04-02 | 2026-03-06
F-0099 | M-0122 | V-0193 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Net Interest Income Volume Model v2). | Medium | Data | Open | U-202 | 2025-10-01 | 2026-04-23
F-0100 | M-0122 | V-0193 | Segmentation not revisited since development | Segmentation not revisited since development (Net Interest Income Volume Model v2). | Low | Methodology | Open | U-202 | 2026-02-10 | 2026-05-03
F-0101 | M-0123 | V-0195 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Student Lending PD Model v3). | Medium | Data | Open | U-203 | 2025-10-27 | 2026-01-31
F-0102 | M-0124 | V-0197 | Production code differs from the validated version | Production code differs from the validated version (Mortgage Liquidity Model). | Medium | Implementation | Closed | U-203 | 2026-03-11 | 2026-10-15 | 2026-09-30
F-0103 | M-0124 | V-0197 | Production code differs from the validated version | Production code differs from the validated version (Mortgage Liquidity Model). | Low | Implementation | Closed | U-203 | 2026-02-28 | 2026-07-22 | 2026-07-21
F-0104 | M-0125 | V-0198 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Loss Model v2). | Critical | Data | Open | U-205 | 2026-05-18 | 2026-08-29
F-0105 | M-0125 | V-0198 | Assumption log incomplete | Assumption log incomplete (CRE Loss Model v2). | Medium | Documentation | Open | U-205 | 2025-10-29 | 2026-01-19
F-0106 | M-0126 | V-0199 | Segmentation not revisited since development | Segmentation not revisited since development (Small Business Rating Model v2). | Low | Methodology | Open | U-202 | 2026-07-05 | 2026-12-02
F-0107 | M-0126 | V-0199 | Segmentation not revisited since development | Segmentation not revisited since development (Small Business Rating Model v2). | Medium | Methodology | In Progress | U-202 | 2025-09-08 | 2026-03-04
F-0108 | M-0127 | V-0201 | Production code differs from the validated version | Production code differs from the validated version (Commercial & Industrial LGD Model v2). | Medium | Implementation | In Progress | U-003 | 2025-10-19 | 2026-04-19
F-0109 | M-0131 | V-0205 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Wholesale Funding Deposit Model). | Medium | Data | Closed | U-202 | 2025-12-17 | 2026-04-02 | 2026-03-22
F-0110 | M-0135 | V-0213 | Production code differs from the validated version | Production code differs from the validated version (International CECL Model). | Low | Implementation | In Progress | U-202 | 2026-03-30 | 2026-06-23
F-0111 | M-0135 | V-0213 | Assumption log incomplete | Assumption log incomplete (International CECL Model). | Medium | Documentation | Closed | U-202 | 2026-01-11 | 2026-04-27 | 2026-04-24
F-0112 | M-0135 | V-0213 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (International CECL Model). | Low | Data | Open | U-202 | 2026-01-06 | 2026-05-16
F-0113 | M-0136 | V-0215 | Production code differs from the validated version | Production code differs from the validated version (Wealth Lending Rating Model). | Medium | Implementation | In Progress | U-205 | 2026-05-13 | 2026-09-27
F-0114 | M-0136 | V-0215 | Segmentation not revisited since development | Segmentation not revisited since development (Wealth Lending Rating Model). | Low | Methodology | Open | U-205 | 2026-03-14 | 2026-09-20
F-0115 | M-0139 | V-0221 | Production code differs from the validated version | Production code differs from the validated version (Card IFRS 9 Model). | Medium | Implementation | Closed | U-204 | 2025-12-06 | 2026-03-01 | 2026-02-23
F-0116 | M-0145 | V-0228 | Production code differs from the validated version | Production code differs from the validated version (Consumer IFRS 9 Model v3). | Medium | Implementation | Closed | U-203 | 2026-05-07 | 2026-11-18 | 2026-09-30
F-0117 | M-0148 | V-0234 | Production code differs from the validated version | Production code differs from the validated version (HELOC PD Model). | Medium | Implementation | Closed | U-201 | 2026-06-18 | 2026-09-20 | 2026-09-04
F-0118 | M-0148 | V-0234 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (HELOC PD Model). | Low | Data | Closed | U-201 | 2026-04-16 | 2026-09-20 | 2026-09-15
F-0119 | M-0149 | V-0235 | Production code differs from the validated version | Production code differs from the validated version (Non-maturity Deposit Deposit Model). | Medium | Implementation | In Progress | U-205 | 2025-09-02 | 2026-02-08
F-0120 | M-0149 | V-0235 | Production code differs from the validated version | Production code differs from the validated version (Non-maturity Deposit Deposit Model). | Medium | Implementation | In Progress | U-205 | 2026-01-30 | 2026-04-23
F-0121 | M-0153 | V-0241 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Student Lending Rating Model). | Medium | Data | Open | U-201 | 2026-05-23 | 2026-11-05
F-0122 | M-0153 | V-0241 | Production code differs from the validated version | Production code differs from the validated version (Student Lending Rating Model). | Low | Implementation | Closed | U-201 | 2026-02-02 | 2026-04-10 | 2026-03-23
F-0123 | M-0155 | V-0245 | Production code differs from the validated version | Production code differs from the validated version (Deposit Volume Volume Model v2). | Medium | Implementation | Open | U-203 | 2026-06-08 | 2027-01-21
F-0124 | M-0155 | V-0245 | Assumption log incomplete | Assumption log incomplete (Deposit Volume Volume Model v2). | Medium | Documentation | In Progress | U-203 | 2026-01-26 | 2026-08-03
F-0125 | M-0156 | V-0247 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Q-factor Model v2). | Medium | Data | Open | U-003 | 2026-03-14 | 2026-08-18
F-0126 | M-0166 | V-0259 | Segmentation not revisited since development | Segmentation not revisited since development (Deposit Volume Volume Model v3). | Medium | Methodology | In Progress | U-205 | 2026-05-25 | 2026-10-08
F-0127 | M-0166 | V-0259 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Deposit Volume Volume Model v3). | Medium | Data | Closed | U-205 | 2026-08-24 | 2027-02-05 | 2026-09-30
F-0128 | M-0166 | V-0259 | Production code differs from the validated version | Production code differs from the validated version (Deposit Volume Volume Model v3). | Medium | Implementation | In Progress | U-205 | 2026-07-18 | 2026-11-17
F-0129 | M-0167 | V-0260 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Consumer RWA Model v2). | Critical | Data | Closed | U-003 | 2026-03-08 | 2026-08-11 | 2026-08-10
F-0130 | M-0168 | V-0262 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Wealth Lending EAD Model). | Medium | Performance | Closed | U-003 | 2026-06-23 | 2027-01-21 | 2026-09-30
F-0131 | M-0168 | V-0262 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Wealth Lending EAD Model). | Medium | Data | Open | U-003 | 2026-07-09 | 2026-12-11
F-0132 | M-0168 | V-0262 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Wealth Lending EAD Model). | Medium | Data | In Progress | U-003 | 2026-01-15 | 2026-06-15
F-0133 | M-0170 | V-0266 | Assumption log incomplete | Assumption log incomplete (Operating Expense Climate Model v3). | Medium | Documentation | In Progress | U-204 | 2026-02-19 | 2026-04-24
F-0134 | M-0170 | V-0266 | Assumption log incomplete | Assumption log incomplete (Operating Expense Climate Model v3). | Medium | Documentation | Open | U-204 | 2025-12-21 | 2026-07-10
F-0135 | M-0170 | V-0266 | Assumption log incomplete | Assumption log incomplete (Operating Expense Climate Model v3). | Low | Documentation | In Progress | U-204 | 2026-07-31 | 2026-10-18
F-0136 | M-0171 | V-0268 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial IFRS 9 Model v2). | Critical | Data | Open | U-204 | 2025-10-07 | 2026-04-20
F-0137 | M-0171 | V-0268 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial IFRS 9 Model v2). | Medium | Data | Open | U-204 | 2025-11-19 | 2026-04-04
F-0138 | M-0171 | V-0268 | Production code differs from the validated version | Production code differs from the validated version (Commercial IFRS 9 Model v2). | Medium | Implementation | Open | U-204 | 2026-06-26 | 2026-12-03
F-0139 | M-0172 | V-0270 | Assumption log incomplete | Assumption log incomplete (Securities Reserve allocation Model v2). | Medium | Documentation | Open | U-206 | 2026-05-11 | 2026-10-13
F-0140 | M-0172 | V-0270 | Segmentation not revisited since development | Segmentation not revisited since development (Securities Reserve allocation Model v2). | Medium | Methodology | Open | U-206 | 2026-01-24 | 2026-07-23
F-0141 | M-0179 | V-0282 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Auto Loan Scorecard Model). | Medium | Data | In Progress | U-205 | 2025-09-24 | 2026-04-07
F-0142 | M-0179 | V-0282 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Auto Loan Scorecard Model). | Medium | Performance | Open | U-205 | 2026-08-27 | 2026-11-19
F-0143 | M-0180 | V-0284 | Assumption log incomplete | Assumption log incomplete (Consumer Scenario Model v2). | Low | Documentation | Open | U-203 | 2026-06-12 | 2026-10-26
F-0144 | M-0180 | V-0284 | Segmentation not revisited since development | Segmentation not revisited since development (Consumer Scenario Model v2). | Low | Methodology | In Progress | U-203 | 2025-09-13 | 2026-02-22
F-0145 | M-0181 | V-0286 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Securities IFRS 9 Model v2). | Low | Data | Open | U-204 | 2026-03-04 | 2026-08-31
F-0146 | M-0181 | V-0286 | Assumption log incomplete | Assumption log incomplete (Securities IFRS 9 Model v2). | Medium | Documentation | In Progress | U-204 | 2026-02-06 | 2026-08-20
F-0147 | M-0182 | V-0288 | Assumption log incomplete | Assumption log incomplete (Deposit Volume Expense Model). | Medium | Documentation | Closed | U-202 | 2026-01-09 | 2026-06-28 | 2026-06-05
F-0148 | M-0182 | V-0288 | Assumption log incomplete | Assumption log incomplete (Deposit Volume Expense Model). | Medium | Documentation | Closed | U-202 | 2026-04-14 | 2026-11-04 | 2026-09-30
F-0149 | M-0185 | V-0294 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Card Q-factor Model v2). | Low | Data | Open | U-205 | 2026-07-09 | 2026-09-10
F-0150 | M-0188 | V-0299 | Segmentation not revisited since development | Segmentation not revisited since development (Branch Expense Model v2). | Medium | Methodology | In Progress | U-201 | 2025-12-08 | 2026-03-23
F-0151 | M-0192 | V-0306 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Treasury ALM/IRR Model v4). | Medium | Performance | In Progress | U-204 | 2026-04-26 | 2026-08-21
F-0152 | M-0192 | V-0306 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Treasury ALM/IRR Model v4). | Medium | Performance | Closed | U-204 | 2026-08-17 | 2027-03-23 | 2026-09-30
F-0153 | M-0193 | V-0308 | Segmentation not revisited since development | Segmentation not revisited since development (Wholesale Funding Liquidity Model v3). | Medium | Methodology | Open | U-206 | 2026-02-11 | 2026-04-24
F-0154 | M-0195 | V-0312 | Assumption log incomplete | Assumption log incomplete (Enterprise Capital Model v2). | Medium | Documentation | In Progress | U-201 | 2026-08-06 | 2027-02-02
F-0155 | M-0197 | V-0316 | Assumption log incomplete | Assumption log incomplete (Wealth Lending PD Model v3). | Low | Documentation | Closed | U-201 | 2025-09-20 | 2026-02-03 | 2026-01-17
F-0156 | M-0197 | V-0316 | Assumption log incomplete | Assumption log incomplete (Wealth Lending PD Model v3). | Low | Documentation | Closed | U-201 | 2026-05-31 | 2026-10-07 | 2026-09-12
F-0157 | M-0197 | V-0316 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Wealth Lending PD Model v3). | Low | Performance | Closed | U-201 | 2025-12-05 | 2026-03-18 | 2026-03-07
F-0158 | M-0198 | V-0318 | Assumption log incomplete | Assumption log incomplete (Commercial & Industrial Collections Model). | Low | Documentation | Open | U-205 | 2026-06-12 | 2026-09-23
F-0159 | M-0198 | V-0318 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial & Industrial Collections Model). | Critical | Data | Open | U-205 | 2025-10-16 | 2026-02-22
F-0160 | M-0200 | V-0322 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Fee Income Climate Model). | Medium | Performance | In Progress | U-206 | 2026-08-27 | 2027-01-26
F-0161 | M-0200 | V-0322 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Fee Income Climate Model). | Medium | Data | Closed | U-206 | 2026-03-06 | 2026-06-20 | 2026-06-11
F-0162 | M-0200 | V-0322 | Segmentation not revisited since development | Segmentation not revisited since development (Fee Income Climate Model). | Medium | Methodology | Closed | U-206 | 2026-05-04 | 2026-07-28 | 2026-07-12
F-0163 | M-0201 | V-0324 | Assumption log incomplete | Assumption log incomplete (Operating Expense Revenue Model v2). | Medium | Documentation | In Progress | U-204 | 2026-08-07 | 2026-11-11
F-0164 | M-0201 | V-0324 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Operating Expense Revenue Model v2). | Medium | Data | Closed | U-204 | 2026-04-08 | 2026-10-27 | 2026-09-30
F-0165 | M-0201 | V-0324 | Assumption log incomplete | Assumption log incomplete (Operating Expense Revenue Model v2). | Low | Documentation | In Progress | U-204 | 2026-07-20 | 2027-02-07
F-0166 | M-0205 | V-0332 | Segmentation not revisited since development | Segmentation not revisited since development (CRE Reserve allocation Model v4). | Medium | Methodology | Closed | U-007 | 2026-03-19 | 2026-09-06 | 2026-08-19
F-0167 | M-0205 | V-0332 | Segmentation not revisited since development | Segmentation not revisited since development (CRE Reserve allocation Model v4). | Medium | Methodology | In Progress | U-007 | 2025-10-04 | 2026-01-03
F-0168 | M-0205 | V-0332 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Reserve allocation Model v4). | Medium | Data | Open | U-007 | 2025-10-31 | 2026-06-19
F-0169 | M-0208 | V-0336 | Production code differs from the validated version | Production code differs from the validated version (Loan Volume Revenue Model). | Low | Implementation | Closed | U-205 | 2026-08-14 | 2027-03-11 | 2026-09-30
F-0170 | M-0208 | V-0336 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Loan Volume Revenue Model). | Critical | Performance | Closed | U-205 | 2025-10-09 | 2026-01-19 | 2026-01-05
F-0171 | M-0209 | V-0338 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Trading Book PPNR Model). | Medium | Data | Open | U-003 | 2025-10-28 | 2026-03-22
F-0172 | M-0216 | V-0347 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (CRE Office Rating Model v2). | Low | Performance | Open | U-202 | 2026-06-24 | 2026-09-11
F-0173 | M-0216 | V-0347 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Office Rating Model v2). | Medium | Data | Open | U-202 | 2026-09-09 | 2027-03-08
F-0174 | M-0217 | V-0349 | Production code differs from the validated version | Production code differs from the validated version (Commercial IFRS 9 Model v3). | Medium | Implementation | Closed | U-007 | 2026-03-30 | 2026-10-12 | 2026-09-22
F-0175 | M-0217 | V-0349 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Commercial IFRS 9 Model v3). | Medium | Data | Open | U-007 | 2026-09-02 | 2027-02-28
F-0176 | M-0218 | V-0351 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Office Rating Model v3). | Low | Data | Open | U-201 | 2026-01-23 | 2026-03-24
F-0177 | M-0218 | V-0351 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Office Rating Model v3). | Medium | Data | Open | U-201 | 2026-07-15 | 2027-03-12
F-0178 | M-0221 | V-0357 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Small Business PD Model v2). | Medium | Data | Open | U-204 | 2025-10-04 | 2026-03-21
F-0179 | M-0221 | V-0357 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Small Business PD Model v2). | Low | Data | In Progress | U-204 | 2026-06-05 | 2026-12-10
F-0180 | M-0224 | V-0363 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (CRE Q-factor Model v4). | Medium | Data | Closed | U-201 | 2025-09-01 | 2025-11-21 | 2025-11-15
F-0181 | M-0224 | V-0363 | Segmentation not revisited since development | Segmentation not revisited since development (CRE Q-factor Model v4). | Critical | Methodology | Closed | U-201 | 2026-05-15 | 2026-11-01 | 2026-09-30
F-0182 | M-0224 | V-0363 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (CRE Q-factor Model v4). | Medium | Performance | Closed | U-201 | 2026-02-12 | 2026-09-09 | 2026-08-22
F-0183 | M-0225 | V-0365 | Segmentation not revisited since development | Segmentation not revisited since development (Securities Portfolio ALM/IRR Model v3). | Low | Methodology | Closed | U-003 | 2026-02-23 | 2026-07-06 | 2026-06-07
F-0184 | M-0225 | V-0365 | Assumption log incomplete | Assumption log incomplete (Securities Portfolio ALM/IRR Model v3). | Low | Documentation | In Progress | U-003 | 2026-06-20 | 2026-08-29
F-0185 | M-0225 | V-0365 | Assumption log incomplete | Assumption log incomplete (Securities Portfolio ALM/IRR Model v3). | Low | Documentation | In Progress | U-003 | 2026-02-11 | 2026-10-01
F-0186 | M-0233 | V-0377 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Operating Expense Revenue Model v3). | Medium | Data | Open | U-007 | 2026-05-30 | 2026-08-27
F-0187 | M-0239 | V-0386 | Assumption log incomplete | Assumption log incomplete (Fee Income Expense Model v5). | Low | Documentation | Closed | U-201 | 2026-04-23 | 2026-08-27 | 2026-08-18
F-0188 | M-0239 | V-0386 | Assumption log incomplete | Assumption log incomplete (Fee Income Expense Model v5). | Low | Documentation | Open | U-201 | 2025-09-07 | 2026-03-21
F-0189 | M-0242 | V-0391 | Assumption log incomplete | Assumption log incomplete (Commercial Q-factor Model v2). | Critical | Documentation | Open | U-206 | 2025-11-24 | 2026-07-19
F-0190 | M-0243 | V-0393 | Assumption log incomplete | Assumption log incomplete (Treasury Prepayment Model v5). | Medium | Documentation | In Progress | U-003 | 2026-09-05 | 2027-01-12
F-0191 | M-0243 | V-0393 | Assumption log incomplete | Assumption log incomplete (Treasury Prepayment Model v5). | Medium | Documentation | In Progress | U-003 | 2026-03-26 | 2026-06-18
F-0192 | M-0244 | V-0395 | Production code differs from the validated version | Production code differs from the validated version (Credit Card PD Model v5). | Low | Implementation | Open | U-201 | 2026-08-05 | 2027-02-25
F-0193 | M-0244 | V-0395 | Production code differs from the validated version | Production code differs from the validated version (Credit Card PD Model v5). | Critical | Implementation | Open | U-201 | 2025-10-13 | 2026-06-07
F-0194 | M-0249 | V-0402 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Deposit Volume Climate Model v4). | Medium | Data | In Progress | U-205 | 2026-01-26 | 2026-05-18
F-0195 | M-0249 | V-0402 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Deposit Volume Climate Model v4). | Medium | Performance | In Progress | U-205 | 2026-02-08 | 2026-05-31
F-0196 | M-0249 | V-0402 | Segmentation not revisited since development | Segmentation not revisited since development (Deposit Volume Climate Model v4). | Critical | Methodology | Closed | U-205 | 2026-08-27 | 2027-04-05 | 2026-09-30
F-0197 | M-0250 | V-0404 | Production code differs from the validated version | Production code differs from the validated version (Residential Mortgage Collections Model). | Low | Implementation | Closed | U-201 | 2026-01-09 | 2026-07-21 | 2026-07-15
F-0198 | M-0250 | V-0404 | Production code differs from the validated version | Production code differs from the validated version (Residential Mortgage Collections Model). | Medium | Implementation | Open | U-201 | 2026-08-02 | 2027-02-13
F-0199 | M-0250 | V-0404 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Residential Mortgage Collections Model). | Low | Data | Open | U-201 | 2026-04-26 | 2026-07-05
F-0200 | M-0252 | V-0407 | Source extract does not reconcile to the ledger | Source extract does not reconcile to the ledger (Deposit Volume Revenue Model v2). | Medium | Data | In Progress | U-206 | 2026-02-17 | 2026-08-07
F-0201 | M-0252 | V-0407 | Segmentation not revisited since development | Segmentation not revisited since development (Deposit Volume Revenue Model v2). | Medium | Methodology | Closed | U-206 | 2026-05-10 | 2026-08-14 | 2026-07-21
F-0202 | M-0252 | V-0407 | Production code differs from the validated version | Production code differs from the validated version (Deposit Volume Revenue Model v2). | Low | Implementation | In Progress | U-206 | 2025-11-26 | 2026-03-09
F-0203 | M-0254 | V-0411 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Operating Expense Expense Model v2). | Critical | Performance | Open | U-203 | 2026-04-17 | 2026-12-03
F-0204 | M-0255 | V-0413 | Rank-ordering weakened in the latest period | Rank-ordering weakened in the latest period (Securities CECL Model v2). | Low | Performance | In Progress | U-201 | 2026-03-08 | 2026-06-28
F-0205 | M-0255 | V-0413 | Production code differs from the validated version | Production code differs from the validated version (Securities CECL Model v2). | Medium | Implementation | Open | U-201 | 2026-08-19 | 2027-02-08
F-0206 | M-0255 | V-0413 | Segmentation not revisited since development | Segmentation not revisited since development (Securities CECL Model v2). | Medium | Methodology | Open | U-201 | 2026-04-11 | 2026-06-26

## instructions
column | type | required | allowed values / rule | description | example
finding_id | text | Yes |  |  | F-0001
model_id | text | Yes | must exist in model |  | M-0012
validation_id | text | No | must exist in validation |  | V-0412
title | text | Yes | max 120 chars |  | CRE obligor data gap
description | text | Yes |  |  | 14% of obligor financial statements missing
severity | text | Yes | Critical, Medium, Low |  | Critical
category | text | Yes | Data, Methodology, Documentation, Implementation, Performance, Monitoring |  | Data
status | text | Yes | Open, In Progress, Deferred, Closed, Accepted Risk, Rejected |  | Open
owner_id | text | Yes | must exist in app_user |  | U-003
raised_date | date | Yes |  |  | 2025-11-15
due_date | date | Yes | Not before raised_date |  | 2026-06-30
closed_date | date | Conditional | Required when the status is closed
root_cause | text | No
management_response | text | No
remediation_action | text | No
Dates as YYYY-MM-DD. Yes/no as Y or N. Lists separated by ';'. Keep the header row as is; column order does not matter. Re-importing an existing ID updates that record.